CONTENTS

[CAPITAL REGION 2](#_Toc430420262)

[1.1AIRPORT 2](#_Toc430420263)

[1.2.NHAI 3](#_Toc430420264)

[1.3. PLANNING 3](#_Toc430420265)

[2. CAPITAL CITY 3](#_Toc430420266)

[2.1. LAND 3](#_Toc430420267)

[2.2 SOCIAL DEVELOPMENT 3](#_Toc430420268)

[2.3.PLANNING: 4](#_Toc430420269)

[2.4. INFRASTRUCTURE: 4](#_Toc430420270)

[2.5. RIVER DEVP 4](#_Toc430420271)

[2.6.GOVERNANCE 5](#_Toc430420272)

[2.7.FINANCING 5](#_Toc430420273)

[2.8. ECONOMIC DEVELOPMENT 6](#_Toc430420274)

[2.9. OCT 22 6](#_Toc430420275)

# CAPITAL REGION

## 1.1AIRPORT

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Action** | **Due date** | **Week progress** | **Status** |  |
| **AIRPORT** | Get consent forms after notification and close land pooling in 30 days | 10th Oct, 15; | Land schedules prepared for airport extension. Land schedules under preparation for shifting of irrigation canal. | LA notification u/s 4(1) under LA R&R Act 2013 to be issued.  Notification under LPS rules to be issued for the extent already notified under LA. |  |
| Report on interim terminal will be submitted in 7 weeks | 5th Nov, 15 |  |  |  |
| Call all the operators and schedule a meeting with Hon'ble CM with regard to construction of 10 new parking bays. | 28th Oct, 15 |  |  |  |
| Prepare an iconic flyover design between NH and airport approach road along with feasibility of connecting to Machilipatnam NH (**Action:** **Commissioner, CRDA)** | 10th, Oct, 15 | Concept designs for Trumpet have been prepared; to be forwarded to Airport authorities for their vetting. Feasibility of connecting to Machilipatnam to be studied. Target : 10th Oct. |  |  |
| Present the final report on expansion of runway by M/s. EIL to the Hon'ble CM | 28th Feb, 17 |  |  |  |
|  | 9.1 notices to be given and land shall be taken position. The Diversion process of Eluru Canal of 7 Kms length shall be completed in 45 days. **(Action: Collector, Krishna & Prl. Secretary, WR)** |  |  |  |  |
|  | The required land shall be taken advance position and re-routing shall be completed in 45 days. (Action: Spl. CS, T, R&B & Collector, Krishna & Prl. Secretary, WR) |  |  |  |  |
|  | Examine feasibility to connect Gannavaram Airport to Machilipatnam NH (Action: Spl. CS, T, R&B) |  |  |  |  |

## 1.2.NHAI

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **Action** | **Due date** | **Week progress** | **Status** |
| **NHAI** | Complete re-carpet of the road from Airport to Varadhi (22 Kms) in 2 weeks **(Action: PD, NHAI)** | 30th, Sep, 15 |  |  |
| Invite all the stakeholders to discuss the 6 laning of Chennai - Visakhapatnam Highway. **(Action: PD, NHAI)** |  |  |  |

## 1.3. PLANNING

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Action** | **Due date** | **Week progress** | **Status** |  |
| **PLANNING** | Provide draft alignment of outer ring road to R & B Dept. as Govt. of India is ready to fund it **(Action: Commissioner, CRDA)** | 16th, Sep, 15 | Draft will be dispatched on 18th Sept. |  |  |

# 2. CAPITAL CITY

## 2.1. LAND

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Action** | **Due date** | **Week progress** | **Status** |  |
| **LAND** | Explore land pooling and notify in 3 villages viz., i) Pedaparimi, ii) Harichandrapuram & iii) Vaddamanu in Tulluru Mandal for 6,000 acres approximately, if landowners come forward to participate in LPS **(Action: Collector, Guntur)** |  | Negotiations are on with the farmers. |  |  |

## 2.2 SOCIAL DEVELOPMENT

**HOUSING:**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Action** | **Due date** | **Week progress** | **Status** |  |
| **HOUSING** | Study reverse auction procedure while developing housing policy  **(Action: Secy, Housing)** |  |  |  |  |
| Plan strategy for construction of 12,000 houses to Government employees **(Action: Secy, Housing)** |  |  |  |  |

## 2.3.PLANNING:

**MASTER PLAN:**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Action** | **Due date** | **Week progress** | **Status** |  |
| **MASTER PLAN** | Pursue the proposal sent to Govt .of India for integrated transport network by Japan so that it shall reach Japan embassy. |  | Letter has been sent to MOUD on 12th Sept. | Approval of GoI awaited. |  |

## 2.4. INFRASTRUCTURE:

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **Action** | **Due date** | **Week progress** | **Status** |
| **CITY INFRASTRUCTUREURE** | Identify 1 or 2 villages for heritage conservation out of the 29 villages **(Action: Secy, Tourism)** |  |  |  |

## 2.5. RIVER DEVP

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **Actio** | **Due date** | **Week progress** | **Status** |
| **RIVER DEVP** | Assess sand requirement for: i) Construction, ii)flat form upgrading as work will start from October for dredging **(Action: Prl. Secy, WR & Commissioner, CRDA)** | 21th Sept | Under progress. |  |
| Prepare implementation plan for canal development in Vijayawada **(Action: Commissioner, CRDA)** | 19th Sept | Concept plan for beautification of Bandar Canal 5 km from regulator is under process. |  |

## 

## 2.6.GOVERNANCE

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **Action** | **Due date** | **Week progress** | **Status** |
| **GOVERANCE** | Addl. Commissioner to be posted for APCRDA **(Action: Prl. Secy to CM)** |  |  |  |
| Take steps to shift Govt. Machinery from Hyderabad to Vijayawada since the Jawahar Reddy Committee has given figures that 12,866 employees of AP Government are identified for shifting. |  |  |  |
| Consider available space in 86 structures like Medha Towers, Rain Tree park etc. identified by both Krishna& Guntur collectors, either for office use or residential use based on R&B norms in Vijayawada and Guntur area. |  |  |  |
|  | Prepare schedule of CM's visit to Singapore **(Action: Secy, CRDA, Commnr, CRDA)** |  |  |  |

## 2.7.FINANCING

**INFRASTRUCTURE FINANCING**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **Action** | **Due date** | **Week progress** | **Status** |
| **INFRASTRUCTURE FINANCING** | Work out cost of infrastructure of Capital City **(Action: Commissioner, CRDA)** |  | Prepared. |  |

## 

## 2.8. ECONOMIC DEVELOPMENT

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **Action** | **Due date** | **Week progress** | **Status** |
| **URBAN DEVEP** | Improve beautification of canals, parks, NH and other peripheral areas and make it noticeable:  **(Action: CE, Director Parks/CRDA.)** | 20th November | Work under progress for NH regarding laying of kerb stone, laying of WMM, paving. For canals & parks concept plan under preparation. | Hydraulic particulars collected from irrigation department have been handed over to planning wing. |
| Prepare Calendar of events in Vijayawada **(Action: Secy, YAT &C)** |  |  |  |

## 2.9. OCT 22

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **Action** | **Due date** | **Week progress** | **Status** |
| **OCT, 22** | Finalize site for foundation stone to be laid on Oct 22 in public area where a park shall come around. **(Action: Collector, Guntur)** |  | To be decided. A coordination meet need to be convened. |  |
| In view of the shortage of time directly invite a good architect for designing pylon and initiate construction. |  | To be decided. A coordination meet need to be convened. . |  |